## Sheet1
TASK | ESTIMATED TIME (HOURS) | COMPLETED
Write schedule and determine tasks | 2 | x
R & D setting boards and pieces-one piece per place, perpendicular to board MVP | 4 | x
R & D websocket authentication and room creation | 2 | x
diagram UI concepts | 2 | x
make GameArea component, Board component, Piece component | 4 | x
R&D pop-ups in bootstrap for click to click movement | 2 | x
implement click to click movement on and off board | 2 | x
Write Box Component for add and removing components from the GameArea | 2 | x
Catch up | 2 | x
R & D Dice roller | 2 | x
Write dice roller component | 4 | x
R&D player hands | 2 | x
catch up | 2 | x
Write hand component | 4 | x
Write ddm and ddl for users in the back end | 1 | x
write a user log/back end data/domain/controller/ | 3 | x
write user back-end security features | 2 | x
test user data layer | 2 | x
test user domain layer | 2 | x
write ddm and ddl for game objects | 2 | x
catch up | 2 | x
write and test data for game objects | 3 | x
write and test domain for game objects | 3 | x
write controller for data game objects | 2 | x
write web socket for spring parts | 2 | x
write user front-end login and authentication | 4 | x
catch up | 2 | x
write add game components front end for admins | 4 | x
write create a game instance form component for users in front end | 2 | x
write user dashboard ui | 4 | x
write user game dashboard ui | 4 | x
make presentation | 2 | x
test and catch up if needed | remaining time, not much really | x
total time | 82